## Task team
Item | Task team | Activity | Owner | Indicative completion date | Actual Completion date
31 | EuroArgo | Management of the Euro-Argo ERIC | S Pouliquen | end 2019
32 | EuroArgo | Enhance communication and outreach (incl. scientific community) | C Gourcuff with Euro-Argo ERIC Management bord | 3 newsletter per year Periodic Newsletter
33 | EuroArgo | Coordination of Euro-Argo float deployment and float monitoring activities | R Cancouet with Euro-Argo ERIC Management bord | Fisrt plan mid March , Continuous update through the year
34 | EuroArgo | Development of the Euro-Argo implementation plan including the extensions of Argo | R Cancouet with Euro-Argo ERIC Management bord | Updated at each Management board
35 | EuroArgo | Organize the work of the ERIC for the EU projects where Euro-Argo is involved
| EuroArgo | Euro-Argo ERIC 5 year evaluation | S Pouliquen with the ERIC Office and the Management Board | "5 year Activity" report and "2020-2025 Actvity plan" end April 2019 Scientific and Technical Advisory board eveluation end June 2019 EA ERIC Council decision end June 2019
36 | EuroArgo | User Workshop | The ERIC Office with the Euro-Argo-Rise Executive Board | October 2019

## Working Groups
Item | Working Group | Activity | Owner | Indicative completion date | Actual Completion date
9 | DATAMEQ | Improvement of the service to users both in NRT and delayed mode using the CMEMS/ROOS, SDN/NODCs and EMODnet infrastructures | SeaDataCloud, CMEMS INSTAC and EMODNET Physics and Chemistry lots projects | continuous action
10 | DATAMEQ | Foster interoperability between the systems by implementing and improving if necessary the available standards in coherence with international landscape. Benefit from ENVRI-FAIR project started in January 2019 and SeaDataCloud project | ENVRi-FAIR Marine Domain partners | Next DataMEQ meeting in 2021
11 | DATAMEQ | Develop a Data Policy for EuroGOOS members | V Fernandez with the help of DataMEQ partners | First Draft at EuroGOOS GA in May 2019
12 | DATAMEQ | Facilitate interaction with providers by establishing a win-win relation | EMODNET with the help of CMEMS INSTAc and EuroGOOS office | continuous action
13 | DATAMEQ | Propose priorities to enhance FAIRness of existing networks fdata system based on analysis made in ENVRI-FAIR | ENVRi-FAIR Marine Domain partners | Early 2020