|  | 2018 Progress review |  | 2019 Workplan |  |  |
| --- | --- | --- | --- | --- | --- |
| Activities | What | Who | What | Who | When |
| BOOS Projects |  |  |  |  |  |
| BOOS AM | Hosted by EuroGOOS, Workshop on BOOS external cooperation | DMI, BOOS-SG | -Will be hosted by IOW -1d WS on coastal climate change and earth system sci. -0.5d National + project reporting -0.5d Business meeting | DMI, SG IOW All All | Late May –June19 |
| BOOS ftp TT | A decision was made that the ftp network will stay as it is but MSI will investigate the option changing to sftp | MSI | N/A | N/A |  |
| BOOS WebWG | - BOOS-AM documents on the web - BALMFC quality info. on the web - Implementation plan of BOOS Web upgrade (draft is ready) | BSH, DMI, SMA | BOOS web upgrade (Plan and actions) | Jan, BOOS WebWG | 2019 |
| BOOS-MME | - Extending number of stations for data exchange – on-going - Implementation plan – TBD | BSH+BALMFC members, FCOO, IOPAN | -MME for Extended number of stations - Implementation plan -MME method improvement | BSH+MME partners FMI+BSH All | 2019 |
| BOOS-Cal/val | - use MFC cal/val toolbox for BOOS cal/val (skype meetings) - change current protocol (Metlab) to python - BOOS cal/val team formed, BSH lead - Some partners have started to use the cal/val toolbox | BSH, MSI+Cal/val partners | -More partners use the common cal/val toolbox -An implementation plan -Joint development of cal/val toolbox using python | Thorger Cal/val team members | May 2019 |
| BOOS-DA | - PDAF cooperation: weekly meetings, developing PDAF-NEMO and PDAF-HBM (SST only, done) - BOOS DA team formed, Lars Axell lead | DMI, BSH, FMI, SMHI | -PDAF-NEMO operational -An implementation plan -Continue of PDAF cooperation | Adam Nord Lars Axell J.She+PDAF team members | May 2019 |
| BOOS Ship data NRT delivery | - Skype meetings - IOPAN NRT data delivery done - Implementation plan – TBD | SMHI, IOW, IOPAN (Task leader is in maternity leave) | Ship data NRT delivery (Plan & actions, with 1-2 more partners) | Johanna Linders’ replacement | 2019 |
| BOOS observing network optimization | - Assessment of BOOS observations (conf. paper) - CMEMS in-situ requirement (report and a ms) - OceanObs paper on “Integrated coastal and biological observations” (ms); - FMI and IOPAN are operating Argo floats in the Baltic. Areas covered: Gotland deep, Bothnian Sea, Bothnian Bay, Bornholm deep | BOOS SG (J. She lead), FMI | - Finalize the CMEMS and BOOS-EMB paper - Further exploring potential BOOS observing system optimization - Argo floats are part of continuous monitoring of the Baltic Sea. Floats in the Gotland Deep, Bothnian Sea and Bothnian Bay are replaced with a new one after c. one year measurement cycle. Measurements every 7 days, data available online through Coriolis | J.She + BOOS SG | 2019 |
| External cooperation |  |  |  |  |  |
| BOOS-HELCOM | - use operational products for HELCOM - NRT delivery of HELCOM ship data - Assimilating HELCOM data - Joint EuroSEA proposal, HELCOM support letter | DMI, MSI, SMHI | -Find new funding opportunities -Join HELCOM meetings | J. She, U. Lips BOOS-SG All partners | Feb. 2019 2019 2019 |
| BOOS-CMEMS | - BALMFC quality products on BOOSweb - Contribute to CMEMS in-situ requirement report | BSH, MSI DMI | -Improved BALMFC presentation on BOOS-Web | BSH+other BALMFC partners | 2019 2019 |
| BOOS-EMODnet | Baltic Sea Checkpoint: data adequacy assessment report | DMI, FMI, TTU, KU, SMA, SMHI | -Promote BOOS in EMODnet as a SG member -EU-CN cooperation on marine data | J.She | 2019 |
| BOOS-Baltic Earth | Joint paper on potential BOOS-Baltic Earth cooperation | BOOS-SG, IOW | -Initiate OO-Climate research interactions via bilateral cooperation | J.She+SG, All | 2019 |
| BOOS-EMB | Joint paper on “Integration coastal and biological obs.” | BOOS-SG, EMB | -Promote potential funding opport. For coastal OO in JPI Ocean | J.She+SG | 2019 |
| BOOS-NOOS | - NOOS Chair gives presentation in BOOS AM and vis verse - Share best practices: NOOS is learning BOOS-BALMFC cooperation; - Identify joint projects with common interests | DMI, MUMM BSH DMI, MUMM | Share NOOS best practices in BOOS (Ensemble forecasting risk index) BOOS-NOOS common projects (River runoff, cal/val) BOOS-NOOS common proposals | Common BOOS-NOOS partners (BSH, DMI, FCOO, HZG) | 2019 |
| BOOS-EOOS | - Contribute to EOOS Forum and EOOS conference - Promote EOOS in OceanObs19 | J. She + BOOS SG | -Responding to EOOS call for action in “national coordination of ocean observing” by initiating relevant actions in BOOS members | All | 2019 |
| Involvement in EuroGOOS WG & TTs |  |  |  |  |  |
| Tidal gauge TT | Contribution to TT | SMHI, DMI, MSI, FMI… | To be planned | SMHI, DMI, MSI, FMI… | 2019 |
| Ferrybox TT | Contribution to TT | SMHI, MSI, SYKE | To be planned | SMHI, MSI, SYKE | 2019 |
| Euro-Argo | FMI and IOPAN are operating Argo floats in the Baltic. Areas covered: Gotland deep, Bothnian Sea, Bothnian Bay, Bornholm deep | FMI, IOPAN | - Argo floats are part of continuous monitoring of the Baltic Sea. Floats in the Gotland Deep, Bothnian Sea and Bothnian Bay are replaced with a new one after c. one year measurement cycle. Measurements every 7 days, data available online through Coriolis | FMI, IOPAN | 2019 |
| Glider TT |  | FMI, MSI | To be planned | FMI, MSI | 2019 |
| CoastalWG | A framework for identifying and filling observational gaps | DMI | -Joint proposals -CoastalWG Work document | DMI, HZG | 2019 |
| SAWG | - Supporting EOOS (EOOS-Forum, EOOS Conference) - Contribution to OceanObs19 (GOOS) on integrated observing (special issues paper) - Forecasting challenge survey - ToR - TBD | DMI, BSH | -ToR | DMI, BSH | May 2019 |
| DMWG | Contribution to WG | SMHI…. | Contribution to WG | SMHI…. | 2019 |
| New proposals |  |  |  |  |  |
| EuroSEA | BOOS-HELCOM integration | DMI, TTU | To be submitted | DMI, TTU |  |
| JERICO3 | Baltic Sea observing (details to be discussed) | FMI, SYKE, SMHI | To be submitted | FMI, SYKE, SMHI |  |
| BALREC | Baltic Sea reconstruction (failed) | SMHI, DMI, HZG |  |  |  |
| H2020 Space call | Oyster restoration | DMI, HZG, CoastalWG | To be submitted | DMI, HZG |  |
| Joint publications |  |  |  |  |  |
| OSR2 (2016) | 4 papers on “extreme low sea level”, “Major Baltic Inflow”, “Extreme events” & “Eutrophication” published | DMI, MSI | N/A | N/A |  |
| Frontier of Mar. Sci | 3 papers on Shallow water Argo obs. | FMI | N/A | N/A |  |
| EuroGOOS conf. proceeding | 3 papers on “BOOS obs. Assessment”, “seamless modelling” & “Emerging service needs” published | DMI | N/A | N/A |  |
| OSR3 (2017) | 3 papers on “Extreme sea ice and its impacts”, “phytoplankton bloom” & “silent storm” under review. | MSI, DMI | Finalizing | MSI, DMI | 2019 |
| OSR4 (2018) | N/A | N/A | 3 papers on “Oxygen OMI”, “Marine Heatwaves” & “Upwelling” to be submitted | MSI, DMI | June 2019 |
| Frontier of Mar. Sci | 3 papers on “CMEMS in-situ”, “integrated observing” and “EMODnet” are under review in OceanObs19 Special issue | DMI, BOOS-SG | Finalizing | DMI, BOOS-SG | 2019 |
|  | 3 papers on “BOOS-BE”, “sea level reconstruction” and “EOF-based reconstruction of SST and SSS” are under review in Baltic Sea Transition special issue | DMI, MSI, IOW BOOS-SG | Finalizing | DMI, MSI, IOW BOOS-SG | 2019 |
| Geosci. Model Dev. | Nemo-Nordic 1.0: a NEMO-based ocean model for the Baltic and North seas – research and operational applications | SMHI, FMI |  |  |  |