|  | EuroGOOS Executive Board-Chairs Meeting 30 January 2019 |
| --- | --- |

FerryBox Task Team work plan 2019

- FB workshop April 2019

What: FB workshop April 2019 in Genoa; general FB activities, also ICOS/FB and EMODnet/FB related presentations

Who: FB task team, international FB operators, ICOS ocean thematic centre, EMODnet physics

When: 24-26 April 2019

Comments/barriers/etc.: Planning slow due to holidays

- EOOS

What: How to be involved and maintain contacts to EOOS pilot activities?

Who: FB task team

When: as needed

Comments/barriers/etc.: Need to improve communication between pilot activities and FB task team

- Data handling and delivery

What: increase the number of data suppliers; improvement and harmonization of quality flagging to both European FB database and EMODnet

Who: FB task team and other FB operators

When: discussion during next FB workshop

Comments/barriers/etc: Need for coordination, time to discuss, implementation and compliance

- Contact/cooperation with other/international SOOP organizations

What: JCOMM-OPS, ICOS, SOOP-XBT

Who: Willi, Andrew, and TBD

When:  JCOMM-OPS meeting April 2019 and will identify further opportunities

Comments/barriers/etc.: Cost/benefit currently unknown

- JERICO-3

What: JERICO-RI proposal

Who: NIVA, HZG, SMHI, SYKE, HCMR... essentially all on FB task team?

When: Writing workshop Jan/Feb 2019; March 2019 deadline

Comments/barriers/etc.: Need to figure out how to fit everyone in and organize some harmonisation/best practices tasks?