## Slide 1
Co-production
Obs & data portal
MME & BMA
Waves
Drift
Elevation, surge
T & S, currents
Data policy
Offshore/private
gaps
Platforms (R.V.)
geographical
…
Rivers
Fresh water
Temperature
BGC, nutrients
Access data ?
E-Hype3
JRC EFAS
AP: EuroGOOS to EEA or JRC!
Ocean Health
Ecosystem
AP : Strategy, new delegates or new NOOS members
EuroGOOS
Office
TT’s, WG’s
ROOSes
NOOS ambassadors
IBI-ROOS
BOOS
MME
Rivers
CAL/VAL
BANOS ?
CMEMS
NWS-MFC
TAC
INS-TAC
Other TAC ?
User uptake
R&D
Training
EOOS

## Slide 2: NOOS ambassadors
DataMEQ: Susanne Tamm (BSH) and Kate Collingride (Cefas)
SAWG: Henning Wehde (IMR) and John Siddorn (UK Met Office)
Coastal WG: Paloma de la Vallée (RBINS)
Ferry box TT: Henning Wehde (IMR)
Glider TT: Holger Brix (HGZ)
Sea mammals: John Siddorn (UK Met Office)
HF Radar: Johannes Schulz-Stellenfleth (HGZ)
Tide gauge: TBD!!! Martin Verlaan (Deltares) and/or someone from BSH?
TPWG, EMSO and ARGO: no ambassadors appointed

## Slide 3: Provisional work programme for 2019 : 24 actions points, 1/3 new
2018.01 | To organise a web-conference in order to decide the best way to get feedbacks on the fitness-for-purpose of the CMEMS products for MSFD assessments and to start an inter-comparison of the different approaches, methodologies and tools used through the NOOS members in their respective MSFD assessments. The creation of a temporary working group could also be discussed. Co-chair to invite CEFAS presenting development in CefMAT (https://emeco.azurewebsites.net/). | E. Garnacho, J. Siddorn and S. Legrand | First half 2019 | Open
2018.02 | To facilitate the engagement of the NOOS community in the CMEMS activities for User Uptake, Training and R&D. This should at least be done by advertising call for tenders and projects. | John Siddorn | Continuous task | Open
2018.03 | To report to the CMEMS Science Advisory Committee that the numerous limitations associated to the current tender framework (administrative burden, strong IPR rules, limitation to 150.000€ on 18 month, obligation to maintain the activities well after the end of the contract, obligation to support the cost of translation of several documents from English to French by a sworn interpreter…) do prevent or strongly discourage ROOSes to submit tenders for the User Uptake, Training and R&D calls. | Glenn Nolan | January 2019 | Open
2018.04 | Update survey of 2017 with focus on Expectation of the relationship between NOOS and CMEMS | Sebastien Legrand | January 2019 | Open
2018.05 | To write the new NOOS strategy document | Steering group | Before summer break 2019 | Open
2018.06 | To write the ToRs of the working group; A new template merging TORs and factsheets is wished less marked by EuroGOOS Create new template | Each NOOS WG and project leader | Before summer break 2019 | Open
2018.07 | To circulate the exact coordinates of the new list of stations used in the BMA. This list should also include Fino1 and 3 | Marc Philippart | Before summer break 2019 | Open

## Slide 4
2018.08 | To study the feasibility of an alarm service in case of extreme high and low level forecast | Marc Philippart | Before annual meeting 2019 | Open
2018.09 | In order to attract interest of MI, to develop a demonstration case with a station at risk of flooding for which there is no tide gauge (e.g. Cork) | Marc Philippart | Before annual meeting 2019 | Open
2018.10 | To redistribute all the BMA forecasts via a ftp site | Marc Philippart | Before annual meeting 2019 | Open
2018.11 | UK met office should implement a ftp box to exchange sea level observations The ftp box should be circulated between forecasters. | John Siddorn Marc Philippart | ASAP | Open
2018.12 | To develop a synoptic map with sea surface anomaly (surge) . | Jacob Nielsen | Annual meeting 2019 | Open
2018.13 | In case of missing observations, to study the feasibility of display BMA forecast on the synoptic maps (both for sea level and sea level anomaly maps) + In any case, add explanation on the page | Jacob Nielsen with the help of Marc? | Annual meeting 2019 | Open
2018.14 | To clarify the conditions and feasibility to add CEFAS wavenet data in the WG. David Pearce is the person at CEFAS to be convinced to get access to the data | Caroline Gautier and Susanne Tamm. | Annual meeting 2019 | Open
2018.15 | To extend the BMA/Matroos to waves forecast... | Caroline Gautier, Marc Philippart and WG members | Annual meeting 2019 | Open
2018.16 | To send to the steering group the list of participants to each task teams | Glenn Nolan | ASAP | Open
2018.17 | NOOS-IBI ROOS collaboration -To contact IBI-ROOS co-chairs to discuss the possibility to co-locate the NOOS and IBI-ROOS annual meeting. The idea is to organise a half-day workshop on the possible synergies between the 2 ROOSes. | Co-chair | First half 2019 | Open

## Slide 5
2018.18 | NOOS-BOOS collaboration: To organise a skype call with interested people to discuss possible NOOS/BOOS collaborations on BMA. Person of contact in BOOS : Laura Tuomi | Martin Verlaan | First half 2019 | open
2018.19 | NOOS-BOOS collaboration on CAL-VAL.: Organise a (skype) meeting with interested people in order to identify possible NOOS-BOOS collaborations on cal.-val. activities (best practices, common python codes, etc.). Person of contact in BOOS : Thorger Brüning | Christine Pequignet | First half 2019 – meeting could be join to the NOWAPS meeting in BSH on mid October 2019 | Open
2018.20 | Short presentation (3 slides) with required information and EuroGOOS priorities, for circulation before redaction of NOOS program | Glenn Nolan | ASAP | Open
2018.20 | EuroGOOS to escalate the need for E-Hype trough agreement with EEA / Copernicus flooding alarm service (Issue : too high fee requested by SMHI) | Glenn Nolan | Annual Meeting 2019 | Open
2018.21 | Provide members with an example of Best Practices in repository | Glenn Nolan | Annual Meeting 2019 | Open
2018.22 | To exchange best practise with the NOOS community and to consider their upload to the IOC repository https://www.oceanbestpractices.net | ALL | Annual meeting 2019 | Open
2018.23 | To develop a strategy to extend NOOS activities to ecology/BGC | Steering group | Annual meeting 2019 | Open
2018.24 | Formulation of a new decision making procedure, allowing to bring the decisions closer to the technical discussion | Steering group | Annual meeting 2019 | Open